## Sheet1
Scope of Work |  | Description | Man Hours | Needed for Website:
Database Table Creation | Users | Website local database | can be done simultaneously with website development | 1 | Logo
| Inventory |  |  | 2 | Privacy Statement
| Buyer's Info |  |  | 3 | Terms and condition statement
| Orders |  |  | 4 | About Us
| Transactions |  |  | 5 | Store Info
| Others |  |  | 6 | Contact Info
Website - Main | Landing Page (View, Actions, Backend) | Main website | 12 | 7 | Inventory template (CSV)
| Search (View, Actions, Backend) |  | 12
| Events |  | 8
| Item Details |  | 8 | List of API's
| Contact Us |  | 4 |  | https://docs.magicthegathering.io/
| About Us |  | 4 |  | https://scryfall.com/
| Anti-robot verifier |  | 4 |  | https://www.tcgplayer.com/
| Purchasing Flow |  | 12
Website - Buyer | Login (View, Actions, Backend) | Buyers Website Access | 8
| Dashboard |  | 4 | Remarks:
| Orders |  | 8 | 1 | Each task contains estimated man-hours. It may exceed or shorten base on the complexity of each task.
| Info |  | 4 | 2 | The scope of work is based on a 4-hour workday, except weekends and holidays.
Website - Seller/Shop | Login (View, Actions, Backend) |  | 8 | 3 | Any possible delays in the estimated man-hours will be relayed immediately.
| Dashboard |  | 4 | 4 | Any changes in the scope of work are subject to discussion.
| Order Management |  | 8
| Inventory Management |  | 12
| Bulk Upload for Inventory |  | 8
| Event Management |  | 8
| User Management |  | 8
API Research | This may affect the man hours depending on the complexity of the API. |  | 20
Dev Testing |  |  | 20
UAT | Actual hours will depend on the end user |  | 20
Server Deployment |  |  | 4
Total Man Hour |  |  | 208