## Sheet1
Actual Man-Hours of Work
Task | Date of Work | Man-Hours |  | Total Man-Hours | 236 | hrs
Database Tables | 2025-12-18 | 4 |  | Running Cost | 41300 | PHP
Base Template (Headers, Footers, Content, Controllers, Model, Plugins, etc.) | 2025-12-18 | 16
Admin - Inventory (List, Add, Edit, etc.) | 2025-12-21 | 16
Main - Homepage | 2025-12-21 | 8
Main - Card Details | 2025-12-23 | 8
Main - Cart | 2025-12-26 | 12
Main - Checkout | 2025-12-28 | 8 |  | What is pending?
Main - Search Page | 2025-12-29 | 12 |  | 1 | QR Ph status on enabling QR codes in coins
Main - Events | 2026-01-03 | 4 |  | 2 | Virtual server for deployment
Main - Contact Us | 2026-01-04 | 4 |  | 3 | About us write up
Main - Checkout Results Redirection | 2026-01-04 | 12
Customer - Login and Register | 2026-01-06 | 8
Customer - Order Management (List, Details, Actions) | 2026-01-08 | 12
Admin - Login | 2026-01-10 | 4
Admin - User Management | 2026-01-10 | 12
Admin and Customer - Role Validation | 2026-01-11 | 8
Admin - Order Management | 2026-01-17 | 16
Admin - Events Management | 2026-01-22 | 8
Admin - Inventory Bulk Upload | 2026-01-25 | 8
Admin - Integration to Scryfall and GA API | 2026-01-26 | 20
Integration of Coins | 2026-02-02 | 20 | Still waiting for the QR enabling in the coins account
Admin - Category Management | 2026-02-11 | 4
Admin - Card Type Management | 2026-02-12 | 4
Admin - Dashboard (Added List of Sales, Refund Function) | 2026-02-15 | 8